## Dashboard
Construction Portfolio - Cost & Schedule Performance
24 projects ¦ 2024-2025 ¦ SAR
KPI | Value
Planned budget (SAR) | 169559000
Actual cost (SAR) | 183428524.85
Cost variance (SAR) | 13869524.85
Portfolio overrun | 8.18%
Packages over budget | 85.25%
Average delay (days) | 14.9
Delay vs overrun correlation | 0.82

## By work package
work_package | packages | planned_sar | actual_sar | variance_sar | avg_overrun_pct | avg_delay_days
Finishing | 19 | 29186000 | 32568325.02 | 3382325.02 | 11.96 | 20.53
MEP | 18 | 24442000 | 27793033.7 | 3351033.7 | 13.22 | 22.78
Electrical | 16 | 24186000 | 26585870.61 | 2399870.61 | 9.41 | 13.94
HVAC | 16 | 26623000 | 28889374.72 | 2266374.72 | 7.41 | 16.19
Steel Structure | 19 | 26526000 | 28398971.45 | 1872971.45 | 6.27 | 13.42
Civil Works | 19 | 19245000 | 20033544.31 | 788544.31 | 4.79 | 8.95
Site Preparation | 15 | 19351000 | 19159405.04 | -191594.96 | 0.8 | 7.27

## By city
city | projects | actual_sar | avg_overrun_pct | on_budget_rate
Jubail | 3 | 24693058.45 | 11.58 | 6.67
Riyadh | 6 | 42268647.51 | 8.82 | 11.11
Dammam | 4 | 22500676.31 | 7.43 | 19.05
Khobar | 8 | 70553335.87 | 6.67 | 16.67
Jeddah | 3 | 23412806.71 | 6.39 | 17.65

## By client
client_type | packages | avg_overrun_pct | avg_delay_days
Government | 61 | 8.73 | 17.56
Private | 57 | 7.1 | 12.53
Semi-Government | 4 | 4.78 | 7.75

## Monthly trend
month | planned_sar | actual_sar | cumulative_variance_sar
2024-01-01 | 12343000 | 13451641.65 | 1108641.65
2024-02-01 | 7987000 | 8707428.71 | 1829070.36
2024-03-01 | 10725000 | 11364316.73 | 2468387.09
2024-04-01 | 7021000 | 7443804.95 | 2891192.04
2024-05-01 | 6011000 | 5973732.12 | 2853924.16
2024-06-01 | 4292000 | 4451118.98 | 3013043.14
2024-07-01 | 8465000 | 8779342.18 | 3327385.32
2024-08-01 | 7093000 | 7713027.48 | 3947412.8
2024-09-01 | 3680000 | 4298457.89 | 4565870.69
2024-10-01 | 15208000 | 16444881.26 | 5802751.95
2024-11-01 | 10016000 | 11061934.6 | 6848686.55
2024-12-01 | 3849000 | 4034937.56 | 7034624.11
2025-01-01 | 6855000 | 7863104.78 | 8042728.89
2025-02-01 | 3582000 | 3760772.88 | 8221501.77
2025-03-01 | 8031000 | 8721772.48 | 8912274.25
2025-04-01 | 17795000 | 19428313.92 | 10545588.17
2025-05-01 | 7351000 | 7909156.48 | 11103744.65
2025-06-01 | 10592000 | 11736977.78 | 12248722.43
2025-07-01 | 6588000 | 7369956.45 | 13030678.88
2025-08-01 | 12075000 | 12913845.97 | 13869524.85

## Top 10 overruns
| project_id | city | work_package | planned_cost_sar | actual_cost_sar | cost_variance_sar | cost_overrun_pct | delay_days
45 | PRJ-010 | Riyadh | Finishing | 2586000 | 3531156.24 | 945156.24 | 36.55 | 56
63 | PRJ-014 | Khobar | HVAC | 2500000 | 3035294.42 | 535294.42 | 21.41 | 17
109 | PRJ-022 | Riyadh | MEP | 2219000 | 2715184.6 | 496184.6 | 22.36 | 34
59 | PRJ-013 | Jubail | Finishing | 1803000 | 2293782.3 | 490782.3 | 27.22 | 65
44 | PRJ-010 | Riyadh | MEP | 2279000 | 2728325.77 | 449325.77 | 19.72 | 32
34 | PRJ-008 | Khobar | HVAC | 2441000 | 2880192.16 | 439192.16 | 17.99 | 9
92 | PRJ-019 | Khobar | Steel Structure | 2391000 | 2805957.5 | 414957.5 | 17.35 | 30
29 | PRJ-007 | Khobar | Electrical | 2342000 | 2724132.99 | 382132.99 | 16.32 | 12
51 | PRJ-011 | Riyadh | MEP | 1478000 | 1802033.02 | 324033.02 | 21.92 | 6
98 | PRJ-020 | Jubail | Steel Structure | 1461000 | 1775992.26 | 314992.26 | 21.56 | 45

## Clean data
| project_id | city | client_type | work_package | start_date | end_date | planned_cost_sar | actual_cost_sar | planned_days | actual_days | cost_variance_sar | cost_overrun_pct | delay_days | schedule_slip_pct | over_budget | month
0 | PRJ-001 | Khobar | Private | Steel Structure | 2024-06-15 | 2024-11-28 | 2108000 | 2111809.64 | 146 | 166 | 3809.64 | 0.18072 | 20 | 13.6986 | TRUE | 2024-06-01
1 | PRJ-001 | Khobar | Private | HVAC | 2024-10-02 | 2025-01-29 | 2069000 | 2123987.71 | 111 | 119 | 54987.71 | 2.6577 | 8 | 7.2072 | TRUE | 2024-10-01
2 | PRJ-001 | Khobar | Private | Civil Works | 2025-05-28 | 2025-07-09 | 774000 | 811472.37 | 42 | 42 | 37472.37 | 4.8414 | 0 | 0 | TRUE | 2025-05-01
3 | PRJ-001 | Khobar | Private | Finishing | 2025-04-03 | 2025-05-17 | 1547000 | 1762114.71 | 37 | 44 | 215114.71 | 13.9053 | 7 | 18.9189 | TRUE | 2025-04-01
4 | PRJ-002 | Riyadh | Government | MEP | 2024-01-21 | 2024-03-30 | 2558000 | 2672060.19 | 58 | 69 | 114060.19 | 4.459 | 11 | 18.9655 | TRUE | 2024-01-01
5 | PRJ-002 | Riyadh | Government | Site Preparation | 2024-02-04 | 2024-07-19 | 746000 | 788099.69 | 152 | 166 | 42099.69 | 5.6434 | 14 | 9.2105 | TRUE | 2024-02-01
6 | PRJ-002 | Riyadh | Government | Steel Structure | 2025-08-20 | 2025-12-26 | 1231000 | 1246668.55 | 127 | 128 | 15668.55 | 1.2728 | 1 | 0.7874 | TRUE | 2025-08-01
7 | PRJ-002 | Riyadh | Government | Finishing | 2024-08-31 | 2024-12-18 | 1787000 | 1958642.9 | 88 | 109 | 171642.9 | 9.6051 | 21 | 23.8636 | TRUE | 2024-08-01
8 | PRJ-003 | Khobar | Private | Electrical | 2024-10-24 | 2025-02-21 | 2359000 | 2642211.72 | 102 | 120 | 283211.72 | 12.0056 | 18 | 17.6471 | TRUE | 2024-10-01
9 | PRJ-003 | Khobar | Private | Civil Works | 2024-08-16 | 2024-10-06 | 1259000 | 1274204.19 | 50 | 51 | 15204.19 | 1.2076 | 1 | 2 | TRUE | 2024-08-01
10 | PRJ-003 | Khobar | Private | Site Preparation | 2024-07-22 | 2024-10-11 | 1649000 | 1539943.42 | 81 | 81 | -109056.58 | -6.6135 | 0 | 0 | FALSE | 2024-07-01
11 | PRJ-003 | Khobar | Private | Steel Structure | 2025-06-29 | 2025-09-18 | 2507000 | 2459597.32 | 81 | 81 | -47402.68 | -1.8908 | 0 | 0 | FALSE | 2025-06-01
12 | PRJ-003 | Khobar | Private | HVAC | 2025-04-18 | 2025-10-29 | 2029000 | 2223504.72 | 175 | 194 | 194504.72 | 9.5862 | 19 | 10.8571 | TRUE | 2025-04-01
13 | PRJ-004 | Jubail | Government | HVAC | 2024-07-02 | 2024-12-09 | 669000 | 714815.16 | 136 | 160 | 45815.16 | 6.8483 | 24 | 17.6471 | TRUE | 2024-07-01
14 | PRJ-004 | Jubail | Government | Civil Works | 2025-02-01 | 2025-07-22 | 1300000 | 1328971.69 | 157 | 171 | 28971.69 | 2.2286 | 14 | 8.9172 | TRUE | 2025-02-01
15 | PRJ-004 | Jubail | Government | MEP | 2025-01-11 | 2025-04-23 | 1225000 | 1488068.29 | 72 | 102 | 263068.29 | 21.475 | 30 | 41.6667 | TRUE | 2025-01-01
16 | PRJ-004 | Jubail | Government | Finishing | 2024-04-17 | 2024-06-02 | 1701000 | 1908236.28 | 38 | 46 | 207236.28 | 12.1832 | 8 | 21.0526 | TRUE | 2024-04-01
17 | PRJ-004 | Jubail | Government | Steel Structure | 2024-07-16 | 2024-09-14 | 1375000 | 1553363.12 | 54 | 60 | 178363.12 | 12.9719 | 6 | 11.1111 | TRUE | 2024-07-01
18 | PRJ-005 | Dammam | Government | Finishing | 2024-03-31 | 2024-07-07 | 1261000 | 1424688.93 | 78 | 98 | 163688.93 | 12.9809 | 20 | 25.641 | TRUE | 2024-03-01
19 | PRJ-005 | Dammam | Government | Steel Structure | 2024-10-16 | 2025-01-22 | 2499000 | 2737900.01 | 89 | 98 | 238900.01 | 9.5598 | 9 | 10.1124 | TRUE | 2024-10-01
20 | PRJ-005 | Dammam | Government | MEP | 2024-04-06 | 2024-09-10 | 847000 | 1129927.98 | 100 | 157 | 282927.98 | 33.4035 | 57 | 57 | TRUE | 2024-04-01
21 | PRJ-005 | Dammam | Government | Electrical | 2024-10-11 | 2025-02-14 | 1563000 | 1630243.23 | 109 | 126 | 67243.23 | 4.3022 | 17 | 15.5963 | TRUE | 2024-10-01
22 | PRJ-006 | Jeddah | Private | Steel Structure | 2024-03-12 | 2024-06-30 | 911000 | 888848.67 | 110 | 110 | -22151.33 | -2.4315 | 0 | 0 | FALSE | 2024-03-01
23 | PRJ-006 | Jeddah | Private | Electrical | 2025-01-30 | 2025-04-23 | 860000 | 1022709.51 | 62 | 83 | 162709.51 | 18.9197 | 21 | 33.871 | TRUE | 2025-01-01
24 | PRJ-006 | Jeddah | Private | Finishing | 2024-05-21 | 2024-07-06 | 956000 | 962500.13 | 41 | 46 | 6500.13 | 0.67993 | 5 | 12.1951 | TRUE | 2024-05-01
25 | PRJ-006 | Jeddah | Private | Site Preparation | 2024-11-28 | 2025-01-26 | 270000 | 301295.61 | 46 | 59 | 31295.61 | 11.591 | 13 | 28.2609 | TRUE | 2024-11-01
26 | PRJ-006 | Jeddah | Private | MEP | 2025-01-15 | 2025-07-01 | 1293000 | 1432625.2 | 150 | 167 | 139625.2 | 10.7985 | 17 | 11.3333 | TRUE | 2025-01-01
27 | PRJ-006 | Jeddah | Private | Civil Works | 2024-11-05 | 2025-03-15 | 884000 | 891576.14 | 121 | 130 | 7576.14 | 0.85703 | 9 | 7.438 | TRUE | 2024-11-01
28 | PRJ-007 | Khobar | Private | Civil Works | 2024-05-14 | 2024-12-07 | 546000 | 631295.9 | 163 | 207 | 85295.9 | 15.622 | 44 | 26.9939 | TRUE | 2024-05-01
29 | PRJ-007 | Khobar | Private | Electrical | 2024-11-07 | 2024-12-31 | 2342000 | 2724132.99 | 42 | 54 | 382132.99 | 16.3165 | 12 | 28.5714 | TRUE | 2024-11-01
30 | PRJ-007 | Khobar | Private | HVAC | 2025-03-17 | 2025-08-27 | 992000 | 1167537.25 | 127 | 163 | 175537.25 | 17.6953 | 36 | 28.3465 | TRUE | 2025-03-01
31 | PRJ-007 | Khobar | Private | Finishing | 2024-06-06 | 2024-08-31 | 1987000 | 2128300.21 | 83 | 86 | 141300.21 | 7.1112 | 3 | 3.6145 | TRUE | 2024-06-01
32 | PRJ-008 | Khobar | Semi-Government | Site Preparation | 2025-08-21 | 2025-12-16 | 1068000 | 1020221.58 | 117 | 117 | -47778.42 | -4.4736 | 0 | 0 | FALSE | 2025-08-01
33 | PRJ-008 | Khobar | Semi-Government | Electrical | 2025-08-06 | 2025-10-28 | 2061000 | 2179486.5 | 74 | 83 | 118486.5 | 5.749 | 9 | 12.1622 | TRUE | 2025-08-01
34 | PRJ-008 | Khobar | Semi-Government | HVAC | 2024-01-11 | 2024-02-16 | 2441000 | 2880192.16 | 27 | 36 | 439192.16 | 17.9923 | 9 | 33.3333 | TRUE | 2024-01-01
35 | PRJ-008 | Khobar | Semi-Government | Civil Works | 2024-03-14 | 2024-09-18 | 1819000 | 1816495.37 | 175 | 188 | -2504.63 | -0.13769 | 13 | 7.4286 | FALSE | 2024-03-01
36 | PRJ-009 | Dammam | Government | MEP | 2025-07-10 | 2025-11-17 | 479000 | 513804.7 | 112 | 130 | 34804.7 | 7.2661 | 18 | 16.0714 | TRUE | 2025-07-01
37 | PRJ-009 | Dammam | Government | Finishing | 2024-11-08 | 2025-03-12 | 499000 | 599491.38 | 100 | 124 | 100491.38 | 20.1386 | 24 | 24 | TRUE | 2024-11-01
38 | PRJ-009 | Dammam | Government | Electrical | 2025-07-08 | 2026-01-13 | 873000 | 928304.69 | 173 | 189 | 55304.69 | 6.335 | 16 | 9.2486 | TRUE | 2025-07-01
39 | PRJ-009 | Dammam | Government | Site Preparation | 2025-03-25 | 2025-07-26 | 538000 | 540434.18 | 123 | 123 | 2434.18 | 0.45245 | 0 | 0 | TRUE | 2025-03-01
40 | PRJ-009 | Dammam | Government | Steel Structure | 2025-08-02 | 2025-09-04 | 1194000 | 1330366.23 | 26 | 33 | 136366.23 | 11.421 | 7 | 26.9231 | TRUE | 2025-08-01
41 | PRJ-009 | Dammam | Government | Civil Works | 2025-05-23 | 2025-10-19 | 1966000 | 1907933.5 | 149 | 149 | -58066.5 | -2.9535 | 0 | 0 | FALSE | 2025-05-01
42 | PRJ-009 | Dammam | Government | HVAC | 2024-03-06 | 2024-07-19 | 223000 | 223373.11 | 127 | 135 | 373.11 | 0.16731 | 8 | 6.2992 | TRUE | 2024-03-01
43 | PRJ-010 | Riyadh | Government | Civil Works | 2025-07-31 | 2025-10-27 | 881000 | 876847.73 | 88 | 88 | -4152.27 | -0.47131 | 0 | 0 | FALSE | 2025-07-01
44 | PRJ-010 | Riyadh | Government | MEP | 2024-09-29 | 2025-01-06 | 2279000 | 2728325.77 | 67 | 99 | 449325.77 | 19.7159 | 32 | 47.7612 | TRUE | 2024-09-01
45 | PRJ-010 | Riyadh | Government | Finishing | 2025-06-12 | 2025-12-25 | 2586000 | 3531156.24 | 140 | 196 | 945156.24 | 36.549 | 56 | 40 | TRUE | 2025-06-01
46 | PRJ-010 | Riyadh | Government | Site Preparation | 2024-12-22 | 2025-04-06 | 341000 | 383787.84 | 98 | 105 | 42787.84 | 12.5478 | 7 | 7.1429 | TRUE | 2024-12-01
47 | PRJ-010 | Riyadh | Government | Electrical | 2024-12-25 | 2025-03-15 | 951000 | 1035333.29 | 73 | 80 | 84333.29 | 8.8679 | 7 | 9.589 | TRUE | 2024-12-01
48 | PRJ-011 | Riyadh | Private | Steel Structure | 2024-02-03 | 2024-06-28 | 231000 | 235748.63 | 134 | 146 | 4748.63 | 2.0557 | 12 | 8.9552 | TRUE | 2024-02-01
49 | PRJ-011 | Riyadh | Private | Electrical | 2025-05-11 | 2025-10-02 | 1218000 | 1389263.85 | 116 | 144 | 171263.85 | 14.0611 | 28 | 24.1379 | TRUE | 2025-05-01
50 | PRJ-011 | Riyadh | Private | Civil Works | 2024-10-29 | 2025-05-08 | 949000 | 956523.36 | 177 | 191 | 7523.36 | 0.79277 | 14 | 7.9096 | TRUE | 2024-10-01
51 | PRJ-011 | Riyadh | Private | MEP | 2025-01-20 | 2025-02-26 | 1478000 | 1802033.02 | 31 | 37 | 324033.02 | 21.9237 | 6 | 19.3548 | TRUE | 2025-01-01
52 | PRJ-012 | Jeddah | Government | Finishing | 2024-02-01 | 2024-03-23 | 2196000 | 2291438.52 | 41 | 51 | 95438.52 | 4.346 | 10 | 24.3902 | TRUE | 2024-02-01
53 | PRJ-012 | Jeddah | Government | HVAC | 2024-07-11 | 2025-01-14 | 2205000 | 2330619.31 | 155 | 187 | 125619.31 | 5.697 | 32 | 20.6452 | TRUE | 2024-07-01
54 | PRJ-012 | Jeddah | Government | MEP | 2025-04-12 | 2025-08-30 | 2120000 | 2352891.01 | 114 | 140 | 232891.01 | 10.9854 | 26 | 22.807 | TRUE | 2025-04-01
55 | PRJ-012 | Jeddah | Government | Civil Works | 2025-08-03 | 2025-09-19 | 1968000 | 2107949.08 | 45 | 47 | 139949.08 | 7.1112 | 2 | 4.4444 | TRUE | 2025-08-01
56 | PRJ-012 | Jeddah | Government | Steel Structure | 2024-10-04 | 2025-03-12 | 2255000 | 2314066.35 | 154 | 159 | 59066.35 | 2.6194 | 5 | 3.2468 | TRUE | 2024-10-01
57 | PRJ-012 | Jeddah | Government | Electrical | 2024-04-09 | 2024-06-19 | 784000 | 747636.16 | 66 | 71 | -36363.84 | -4.6382 | 5 | 7.5758 | FALSE | 2024-04-01
58 | PRJ-013 | Jubail | Government | Steel Structure | 2025-02-15 | 2025-04-10 | 1098000 | 1181369.08 | 53 | 54 | 83369.08 | 7.5928 | 1 | 1.8868 | TRUE | 2025-02-01
59 | PRJ-013 | Jubail | Government | Finishing | 2024-10-03 | 2025-05-23 | 1803000 | 2293782.3 | 167 | 232 | 490782.3 | 27.2203 | 65 | 38.9222 | TRUE | 2024-10-01
60 | PRJ-013 | Jubail | Government | MEP | 2025-05-24 | 2025-12-30 | 1475000 | 1757275.11 | 173 | 220 | 282275.11 | 19.1373 | 47 | 27.1676 | TRUE | 2025-05-01
61 | PRJ-013 | Jubail | Government | Site Preparation | 2024-04-16 | 2024-08-05 | 1518000 | 1496779.62 | 107 | 111 | -21220.38 | -1.3979 | 4 | 3.7383 | FALSE | 2024-04-01
62 | PRJ-013 | Jubail | Government | Civil Works | 2024-05-01 | 2024-06-05 | 1958000 | 2126588.83 | 30 | 35 | 168588.83 | 8.6103 | 5 | 16.6667 | TRUE | 2024-05-01
63 | PRJ-014 | Khobar | Private | HVAC | 2025-04-25 | 2025-07-02 | 2500000 | 3035294.42 | 51 | 68 | 535294.42 | 21.4118 | 17 | 33.3333 | TRUE | 2025-04-01
64 | PRJ-014 | Khobar | Private | MEP | 2025-03-09 | 2025-08-19 | 2591000 | 2735406.17 | 148 | 163 | 144406.17 | 5.5734 | 15 | 10.1351 | TRUE | 2025-03-01
65 | PRJ-014 | Khobar | Private | Electrical | 2024-02-27 | 2024-04-04 | 1607000 | 1838983.67 | 32 | 37 | 231983.67 | 14.4358 | 5 | 15.625 | TRUE | 2024-02-01
66 | PRJ-014 | Khobar | Private | Finishing | 2025-03-12 | 2025-07-03 | 199000 | 202028.45 | 113 | 113 | 3028.45 | 1.5218 | 0 | 0 | TRUE | 2025-03-01
67 | PRJ-014 | Khobar | Private | Site Preparation | 2025-04-24 | 2025-11-14 | 2028000 | 2068576.07 | 167 | 204 | 40576.07 | 2.0008 | 37 | 22.1557 | TRUE | 2025-04-01
68 | PRJ-014 | Khobar | Private | Steel Structure | 2025-03-08 | 2025-09-15 | 516000 | 512346.77 | 169 | 191 | -3653.23 | -0.70799 | 22 | 13.0178 | FALSE | 2025-03-01
69 | PRJ-014 | Khobar | Private | Civil Works | 2025-01-29 | 2025-05-27 | 392000 | 419876.04 | 100 | 118 | 27876.04 | 7.1112 | 18 | 18 | TRUE | 2025-01-01
70 | PRJ-015 | Riyadh | Government | Finishing | 2024-07-06 | 2024-09-15 | 1715000 | 1774412.37 | 66 | 71 | 59412.37 | 3.4643 | 5 | 7.5758 | TRUE | 2024-07-01
71 | PRJ-015 | Riyadh | Government | Steel Structure | 2024-03-29 | 2024-10-20 | 561000 | 586840.56 | 174 | 205 | 25840.56 | 4.6062 | 31 | 17.8161 | TRUE | 2024-03-01
72 | PRJ-015 | Riyadh | Government | HVAC | 2025-07-23 | 2025-11-12 | 1964000 | 2245041.83 | 84 | 112 | 281041.83 | 14.3097 | 28 | 33.3333 | TRUE | 2025-07-01
73 | PRJ-015 | Riyadh | Government | Electrical | 2025-04-13 | 2025-07-20 | 2445000 | 2744025.27 | 80 | 98 | 299025.27 | 12.2301 | 18 | 22.5 | TRUE | 2025-04-01
74 | PRJ-016 | Dammam | Private | Electrical | 2024-11-22 | 2025-01-17 | 477000 | 548071 | 43 | 56 | 71071 | 14.8996 | 13 | 30.2326 | TRUE | 2024-11-01
75 | PRJ-016 | Dammam | Private | HVAC | 2024-09-29 | 2024-11-07 | 209000 | 195920.29 | 39 | 39 | -13079.71 | -6.2582 | 0 | 0 | FALSE | 2024-09-01
76 | PRJ-016 | Dammam | Private | Finishing | 2024-11-05 | 2025-02-17 | 2523000 | 2695999.17 | 96 | 104 | 172999.17 | 6.8569 | 8 | 8.3333 | TRUE | 2024-11-01
77 | PRJ-016 | Dammam | Private | Site Preparation | 2025-04-13 | 2025-08-30 | 2402000 | 2124556.58 | 139 | 139 | -277443.42 | -11.5505 | 0 | 0 | FALSE | 2025-04-01
78 | PRJ-016 | Dammam | Private | Civil Works | 2024-01-26 | 2024-07-09 | 286000 | 306338.13 | 161 | 165 | 20338.13 | 7.1112 | 4 | 2.4845 | TRUE | 2024-01-01
79 | PRJ-016 | Dammam | Private | MEP | 2025-08-22 | 2026-01-15 | 437000 | 468076.09 | 128 | 146 | 31076.09 | 7.1112 | 18 | 14.0625 | TRUE | 2025-08-01
80 | PRJ-017 | Riyadh | Government | Site Preparation | 2025-06-29 | 2025-08-23 | 2136000 | 2191660.66 | 55 | 55 | 55660.66 | 2.6058 | 0 | 0 | TRUE | 2025-06-01
81 | PRJ-017 | Riyadh | Government | MEP | 2024-01-04 | 2024-02-06 | 267000 | 287317.43 | 25 | 33 | 20317.43 | 7.6095 | 8 | 32 | TRUE | 2024-01-01
82 | PRJ-017 | Riyadh | Government | HVAC | 2024-05-26 | 2024-10-22 | 2551000 | 2253347.26 | 149 | 149 | -297652.74 | -11.6681 | 0 | 0 | FALSE | 2024-05-01
83 | PRJ-017 | Riyadh | Government | Civil Works | 2025-04-25 | 2025-09-06 | 318000 | 329157.72 | 128 | 134 | 11157.72 | 3.5087 | 6 | 4.6875 | TRUE | 2025-04-01
84 | PRJ-017 | Riyadh | Government | Steel Structure | 2024-03-09 | 2024-08-18 | 2227000 | 2487938.45 | 133 | 162 | 260938.45 | 11.717 | 29 | 21.8045 | TRUE | 2024-03-01
85 | PRJ-017 | Riyadh | Government | Finishing | 2024-10-29 | 2025-04-26 | 482000 | 574998.53 | 133 | 179 | 92998.53 | 19.2943 | 46 | 34.5865 | TRUE | 2024-10-01
86 | PRJ-018 | Dammam | Private | Finishing | 2025-03-25 | 2025-06-17 | 218000 | 269900.37 | 66 | 84 | 51900.37 | 23.8075 | 18 | 27.2727 | TRUE | 2025-03-01
87 | PRJ-018 | Dammam | Private | HVAC | 2024-02-02 | 2024-05-18 | 1659000 | 1776975.36 | 103 | 106 | 117975.36 | 7.1112 | 3 | 2.9126 | TRUE | 2024-02-01
88 | PRJ-018 | Dammam | Private | Steel Structure | 2024-08-10 | 2025-01-19 | 710000 | 760489.76 | 162 | 162 | 50489.76 | 7.1112 | 0 | 0 | TRUE | 2024-08-01
89 | PRJ-018 | Dammam | Private | Civil Works | 2024-04-20 | 2024-09-11 | 401000 | 387881.62 | 144 | 144 | -13118.38 | -3.2714 | 0 | 0 | FALSE | 2024-04-01
90 | PRJ-019 | Khobar | Private | Finishing | 2024-09-22 | 2025-02-18 | 1192000 | 1374211.83 | 114 | 149 | 182211.83 | 15.2862 | 35 | 30.7018 | TRUE | 2024-09-01
91 | PRJ-019 | Khobar | Private | Electrical | 2024-03-30 | 2024-05-23 | 2456000 | 2639668.81 | 49 | 54 | 183668.81 | 7.4784 | 5 | 10.2041 | TRUE | 2024-03-01
92 | PRJ-019 | Khobar | Private | Steel Structure | 2025-07-22 | 2025-11-27 | 2391000 | 2805957.5 | 98 | 128 | 414957.5 | 17.355 | 30 | 30.6122 | TRUE | 2025-07-01
93 | PRJ-019 | Khobar | Private | Site Preparation | 2024-07-01 | 2024-08-09 | 852000 | 866188.8 | 39 | 39 | 14188.8 | 1.6654 | 0 | 0 | TRUE | 2024-07-01
94 | PRJ-019 | Khobar | Private | Civil Works | 2025-05-19 | 2025-10-03 | 1149000 | 1175483.88 | 123 | 137 | 26483.88 | 2.305 | 14 | 11.3821 | TRUE | 2025-05-01
95 | PRJ-019 | Khobar | Private | MEP | 2024-12-18 | 2025-06-23 | 706000 | 723169.13 | 172 | 187 | 17169.13 | 2.4319 | 15 | 8.7209 | TRUE | 2024-12-01
96 | PRJ-020 | Jubail | Government | Electrical | 2025-01-04 | 2025-05-28 | 1607000 | 1697792.72 | 133 | 144 | 90792.72 | 5.6498 | 11 | 8.2707 | TRUE | 2025-01-01
97 | PRJ-020 | Jubail | Government | Civil Works | 2025-04-17 | 2025-07-02 | 945000 | 1012201.16 | 63 | 76 | 67201.16 | 7.1112 | 13 | 20.6349 | TRUE | 2025-04-01
98 | PRJ-020 | Jubail | Government | Steel Structure | 2025-04-29 | 2025-10-13 | 1461000 | 1775992.26 | 122 | 167 | 314992.26 | 21.56 | 45 | 36.8852 | TRUE | 2025-04-01
99 | PRJ-020 | Jubail | Government | Finishing | 2025-06-15 | 2025-11-01 | 1962000 | 2225873.56 | 111 | 139 | 263873.56 | 13.4492 | 28 | 25.2252 | TRUE | 2025-06-01
100 | PRJ-020 | Jubail | Government | MEP | 2024-11-07 | 2025-03-05 | 1954000 | 2131949.27 | 105 | 118 | 177949.27 | 9.1069 | 13 | 12.381 | TRUE | 2024-11-01
101 | PRJ-021 | Khobar | Private | MEP | 2024-02-09 | 2024-05-09 | 1548000 | 1776182.84 | 76 | 90 | 228182.84 | 14.7405 | 14 | 18.4211 | TRUE | 2024-02-01
102 | PRJ-021 | Khobar | Private | Finishing | 2024-01-09 | 2024-06-21 | 1977000 | 1829213.24 | 164 | 164 | -147786.76 | -7.4753 | 0 | 0 | FALSE | 2024-01-01
103 | PRJ-021 | Khobar | Private | Steel Structure | 2025-02-05 | 2025-05-12 | 1184000 | 1250432.11 | 82 | 96 | 66432.11 | 5.6108 | 14 | 17.0732 | TRUE | 2025-02-01
104 | PRJ-021 | Khobar | Private | Civil Works | 2024-08-06 | 2024-11-19 | 469000 | 529571.37 | 103 | 105 | 60571.37 | 12.915 | 2 | 1.9417 | TRUE | 2024-08-01
105 | PRJ-021 | Khobar | Private | Site Preparation | 2024-03-27 | 2024-08-18 | 1267000 | 1296462.83 | 144 | 144 | 29462.83 | 2.3254 | 0 | 0 | TRUE | 2024-03-01
106 | PRJ-021 | Khobar | Private | HVAC | 2024-08-20 | 2025-01-31 | 1887000 | 2046943.03 | 141 | 164 | 159943.03 | 8.476 | 23 | 16.3121 | TRUE | 2024-08-01
107 | PRJ-021 | Khobar | Private | Electrical | 2025-03-02 | 2025-05-07 | 1813000 | 2034481.31 | 57 | 66 | 221481.31 | 12.2163 | 9 | 15.7895 | TRUE | 2025-03-01
108 | PRJ-022 | Riyadh | Private | HVAC | 2025-08-17 | 2026-02-01 | 2210000 | 2519537.83 | 149 | 168 | 309537.83 | 14.0062 | 19 | 12.7517 | TRUE | 2025-08-01
109 | PRJ-022 | Riyadh | Private | MEP | 2024-01-25 | 2024-05-23 | 2219000 | 2715184.6 | 85 | 119 | 496184.6 | 22.3607 | 34 | 40 | TRUE | 2024-01-01
110 | PRJ-022 | Riyadh | Private | Site Preparation | 2024-10-08 | 2025-01-15 | 1229000 | 1171168.05 | 99 | 99 | -57831.95 | -4.7056 | 0 | 0 | FALSE | 2024-10-01
111 | PRJ-022 | Riyadh | Private | Electrical | 2024-04-25 | 2024-11-05 | 770000 | 783525.89 | 165 | 194 | 13525.89 | 1.7566 | 29 | 17.5758 | TRUE | 2024-04-01
112 | PRJ-023 | Jeddah | Government | MEP | 2025-05-21 | 2025-12-01 | 769000 | 867727.77 | 155 | 194 | 98727.77 | 12.8385 | 39 | 25.1613 | TRUE | 2025-05-01
113 | PRJ-023 | Jeddah | Government | HVAC | 2025-03-10 | 2025-08-02 | 1164000 | 1259637.98 | 128 | 145 | 95637.98 | 8.2163 | 17 | 13.2812 | TRUE | 2025-03-01
114 | PRJ-023 | Jeddah | Government | Steel Structure | 2024-11-19 | 2025-04-28 | 1067000 | 1169419.04 | 140 | 160 | 102419.04 | 9.5988 | 20 | 14.2857 | TRUE | 2024-11-01
115 | PRJ-023 | Jeddah | Government | Civil Works | 2024-08-09 | 2024-11-27 | 981000 | 1143176.23 | 99 | 110 | 162176.23 | 16.5317 | 11 | 11.1111 | TRUE | 2024-08-01
116 | PRJ-023 | Jeddah | Government | Site Preparation | 2025-06-29 | 2025-09-28 | 1401000 | 1328690 | 91 | 91 | -72310 | -5.1613 | 0 | 0 | FALSE | 2025-06-01
117 | PRJ-024 | Khobar | Government | Finishing | 2024-01-06 | 2024-07-22 | 2595000 | 2761335.9 | 167 | 198 | 166335.9 | 6.4099 | 31 | 18.5629 | TRUE | 2024-01-01
118 | PRJ-024 | Khobar | Government | Steel Structure | 2024-04-24 | 2024-07-10 | 1000000 | 989817.4 | 74 | 77 | -10182.6 | -1.0183 | 3 | 4.0541 | FALSE | 2024-04-01
119 | PRJ-024 | Khobar | Government | HVAC | 2024-12-05 | 2025-03-25 | 1851000 | 1892647.3 | 94 | 110 | 41647.3 | 2.25 | 16 | 17.0213 | TRUE | 2024-12-01
120 | PRJ-024 | Khobar | Government | MEP | 2024-06-15 | 2024-09-22 | 197000 | 211009.13 | 89 | 99 | 14009.13 | 7.1112 | 10 | 11.236 | TRUE | 2024-06-01
121 | PRJ-024 | Khobar | Government | Site Preparation | 2025-08-13 | 2026-03-12 | 1906000 | 2041540.11 | 177 | 211 | 135540.11 | 7.1112 | 34 | 19.209 | TRUE | 2025-08-01